## Slide 1: Post Acute Care Interoperability Working Group Deliverables Timeline
Define use case
Identify data model for use case
Develop FHIR Implementation Guide
Develop Reference Implementation
Testing
Prepare for Connectathon
Connectathon

## Slide 2
MONTH | ACTIVITIES
APRIL | Charter: ☒ Develop charter ☒ Vote and approve charter Define use case: ☐ Divide larger use case into tightly-scoped agile pieces ☐ Decide on use case(s) to implement ☐ Identify contributors interested in leading use case groups Identify data model for use case: ☐ Search for existing FHIR IGs for those data models

## Slide 3
MONTH | ACTIVITIES
MAY | Identify data model for use case continued: ☐ Adapt FHIR IGs as needed ☐ Negotiate changes with FHIR IG owners FHIR IG Development: ☐ If necessary, develop new FHIR IGs, to close remaining gaps Reference Implementation iterative development begins ☐ Determine overall architecture and assign owners ☐ Sprint planning ☐ Sprint reviews Testing: ☐ Identify testing frameworks Solicitation of Interest for Sept Connectathon ☐ Document justification and objectives ☐ Document proposed track leads ☐ Document preliminary participant list ☐ Document track orientation and resources ☐ Document system roles ☐ Document scenarios

## Slide 4
MONTH | ACTIVITIES
JUNE | FHIR IG Development: ☐ Fine tuning of FHIR IG Reference Implementation iterative development continues: ☐ Sprint planning ☐ Sprint reviews ☐ Syntactic, semantic functional testing ☐ Working group demonstrations

## Slide 5
MONTH | ACTIVITIES
JULY | FHIR IG Development continued: ☐ Finalize FHIR IGs for use case Reference Implementation iterative development continues: ☐ Sprint planning and review to add functionality ☐ Syntactic, semantic functional testing ☐ Working group demonstrations Prepare for Connectathon ☐ Finalize participant list ☐ Reserve track space / rooms at venue

## Slide 6
MONTH | ACTIVITIES
AUGUST | Reference Implementation iterative development continues: ☐ Sprint planning and review to add functionality ☐ Syntactic, semantic functional testing ☐ Start integration testing ☐ Functionality complete

## Slide 7
MONTH | ACTIVITIES
SEPTEMBER | Reference Implementation iterative development continues: ☐ Fix defects ☐ Syntactic, semantic functional and integration testing Connectathon, September 14-15, 2019 HL7 Working Group Meeting, Atlanta, GA