## Slide 1: Leadership Updates
3/11/2020

## Slide 2: Objectives
Current PACIO Project status
Discuss alignment with existing FHIR Projects
Connectathon preparation

## Slide 3: Current Project Status:
Identifying the Data Model | 
Requirements | 
Search for existing FHIR IG’s for those data models | 
Identify gaps in the data models | 
Decision to adapt or develop new FHIR IG | 
FHIR IG Development | 
Determine which fields will be used | 
Determine which extensions need to be added | 
Determine if cardinalities need to be changed | 
Specify profiles and extensions | 
Specify Queries | 
Testing | 
Reference Implementation Development | 
Build data set | 
Build test set | 
Build initial RI | 
Stand up FHIR server and database server | 
Load all implementation guides, StructureDefinition, ValueSet & CodeSystem to FHIR server | 
Develop ways that clients will need to efficiently query the data | 
Testing | 

## Slide 4: Aligning with existing FHIR Projects
  electronic Long-Term Services and Supports (eLTSS) Implementation Guide (IG)
  IG Goals:
    Identify components or data elements needed for the electronic creation and interoperable exchange of person-centered service plans by health care and HCBS providers, payers and the individuals they serve and
    Field test these data elements within participating organizations’ electronic systems.
  Based on FHIR R4, currently scoped to data commonly found on LTSS service plans.
  Link to Implementation Guide: http://hl7.org/fhir/us/eltss/2019May/

## Slide 5: Aligning with existing FHIR Projects
  eLTSS Reference Implementation
  Altarum Institute is developing the eLTSS reference implementation
    https://github.com/onc-healthit/eLTSS-reference-implementation
  Working with the State of Michigan
  Participated in the Care Planning and Management Track at the September 2019 Connectathon in Atlanta, GA
    https://confluence.hl7.org/display/FHIR/2019-09+Care+Planning+and+Management+Track
    Connectathon use case: https://confluence.hl7.org/display/FHIR/2019-09+Care+Planning+and+Management+Track?preview=/55936474/66914314/Use%20Case%20eLTSS%20FHIR%20Beneficiary%20Care%20Coordinator%2020190903.docx
    Connectathon use case was based on Chronic Kidney Disease Care Management
    Altarum Institute is reviewing the PACIO Project use case and developing recommendations on integration
  Held a discussion with Altarum and eLTSS on merging use cases
  EMI Advisors / State of Missouri
  EMI Advisors is helping the eLTSS project to test the implementation guide with the State of Missouri
  Including FASI data elements

## Slide 6: PACIO – eLTSS Use Case Comparison
Use Case Components | PACIO – Betsy Smith | eLTSS – Betsy Johnson
CarePlan | n/a | Exercise / join a fitness club Snow Emergencies: A shelf stable blizzard meal is delivered to Meals On Wheels clients in early winter. It is to be eaten in the unlikely event of cancellation. Blizzard meals are donated by the Sheboygan Service Club.
Claim | n/a | Cost of service
Condition | Hypertension, hyperlipidemia, stage 3 chronic kidney disease, ischemic heart disease, depression, cataracts, osteoarthritis, type II diabetes | Lack of access to transportation, difficulty bathing self, difficulty performing dressing activity

## Slide 7: PACIO – eLTSS Use Case Comparison (cont’d)
Use Case Components | PACIO – Betsy Smith | eLTSS – Betsy Johnson
Contract | n/a | Service provider signatures
Coverage | n/a | Links to the eLTSS Service Funding Source
Encounter | Sample encounter for Betsy Smith | n/a
EpisodeOfCare | n/a | Connects Beneficiary with Care Manager
Goal | Return to her baseline functional status (independent with a cane) and return home once she can safely do so. | Lose weight, dance at daughter's wedding
Location | Texas, Maryland | 2222 Peachtree Street, Atlanta GA, 30318 7247 Breen St., Springfield IL, 62707

## Slide 8: PACIO – eLTSS Use Case Comparison (cont’d)
Use Case Components | PACIO – Betsy Smith | eLTSS – Betsy Johnson
Medication | Lisinopril 40mg twice a day • Glargine 24 units SQ nightly • Atorvastatin 40mg nightly • Insulin 3 units with each meal • Calcium 500mg daily • Sertraline 25mg nightly • Vitamin D 800IU daily • Tylenol 650mg every 6 hours or as needed • Furosemide 20mg daily • Ferrous Sulfate 325mg three times a day prior to meals | n/a
MedicationRequest | Connects Medication with Patient | n/a
Observation | Bundled Functioal Status, Functional Status, Bundled Cognitive Status, Cognitive Status | Accessing the ICWP Waiver for her current service needs, and would like to remain on ICWP and continue with her current services Able to manage her bills. Has strong family support

## Slide 9: PACIO – eLTSS Use Case Comparison (cont’d)
Use Case Components | PACIO – Betsy Smith | eLTSS – Betsy Johnson
Patient | Betsy Smith, 69-year old white female widow | Betsy Johnson, 63-year old
Practitioner | PCP • Cardiologist Endocrinologist • Nephrologist • Psychiatrist • Ophthalmologist • Retail Pharmacy • Lab Services | Service Provider, Care Manager, Planner, Provider
Questionnaire | n/a | Service Questionnaire
QuestionnaireResponse | n/a | Service QuestionnaireResponse
RelatedPerson | n/a | Jane Daughter, Guardian: William Barrister
RiskAssessment | n/a | Risk for falls
ServiceRequest | n/a | Personal care services, per 15 minutes, non-emergency transportation - encounter/trip, house cleaning

## Slide 10: Proposed Architecture for HL7 Connectathon
Care Setting A EHR
Care Setting B EHR
CMS Pseudo DEL
Mobile/Web Portal
Functional/Cognitive, Care Plan
Functional/Cognitive, Care Plan
Assessments
Assessments
Functional/Cognitive, Care Plan
Functional/Cognitive, Care Plan

## Slide 11: Preparing for the May HL7 Connectathon
Clinical assistance needed for:
Building a use case for the connectathon that aligns PACIO Project, eLTSS, Altarum and EMI advisors work
Generating sample data for the connectathon
Technical assistance needed for:
Writing / reviewing the Implementation Guide
Developing the Reference Implementation
Developing vendor implementations
  Need three independent IG implementations for ballot approval
Testing
  ONC Inferno (servers), AEGIS Touchstone (servers, clients)

## Slide 12: Preparing for May HL7 Connectathon
Task | Volunteer(s)
Participant Recruitment | 
Implementation Guide Development | 
Generate Sample Data | 
Server Reference Implementation | 
Client Reference Implementation | 
Test Scripts | 
Hosting Reference Server | 
Hosting Reference Client | 
Second Implementation (Server, Client) | 
Third Implementation (Server, Client) | 
Connectathon Track Lead | 

## Slide 13: HL7 May Connectathon Timeline
3 April 2020
FHIR Connectathon Track Proposals
16-17 May 2020
HL7 Connectathon
1 May 2020
Reference Implementation Functionally Complete
10 April 2020
Implementation Guide Draft Complete
https://confluence.hl7.org/display/HL7/HL7+Calendars
https://confluence.hl7.org/display/FHIR/2020-05+Connectathon+24

## Slide 14: Balloting Timeline
22 May 2020
FHIR Resource Proposals Due
16 August – 14 September 2020
Ballot Open for Voting
5 July 2020
Notice of Intent to Ballot
FHIR Implementation Guides must be substantially complete
21 June 2020
FHIR Implementation Guide Proposals Due
14 Sept – 28 Sept 2020
Oct – Dec 2020 (estimate)
January 2021 (estimate)
Ballot Triaging
Prioritizing, categorizing, grouping
Ballot Reconciliation
Address all comments and develop responses
STU1 Ballot Approval
Publishing STU1 IG
February 2021 (estimate)
Gain approval from sponsoring work groups
Gain approval of FHIR Management Group and Technical Standards Committee
https://confluence.hl7.org/display/HL7/HL7+Calendars